## PROJECT PROFILE
Defect Tracking Sheet
TMT/TD05/TMP
Project ID | Project_AMS_1
Project Name | Asset Management System
Prepared/Modified by | Role | Date of Preparation
Siri Chandana | Test Engineer | 2018-07-17
Reviewed by | Role | Date of Review
xxx | Test Lead
Approved by | Role | Date of Approval
yyy | Test Manager
Circulation List
Version Number | 2

## DEFECT TRACKING SHEET
Project ID: Project_AMS_1 |  | Project Name :Asset Management System
Defect Id. | Module name | Defect Summary | Defect Description | Defect Category | Detected in Browser | Environment | Defect Severity | Defect Priority | Detected in Release # | Detected in Build # | Reported Date | Reported By | Assigned To | Status | Review type / Test Cycle | Test Case No. | Fixed By | Fixed Date | Verified Date | Verified By | Verified in Release # | Verified in Build # | Attachements | Comments
LOGIN_001 | LOGIN | The name field in the login page is found to accept special characters and digits. | Detailed Description: The name field in the login page is found to accept special characters and digits. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website"http://ndafile:8081/AssetManagementSystem_Spring/index.html". 3. Click on "Click here to login". 4. Enter special characters or numbers in the name field. 5. Click on Submit button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts invalid values in the name field. The application proceeds to the next page.There is no error message shown as expected. | Coding | Internet Explorer | Internal Dev | Medium | High | 1.1 | Build 1.0 | 2018-07-17 | Siri | xxx | ACT | Test Cycle 1 | TC_NAME_03
LOGIN_002 | LOGIN | The password field in the login page is found to accept less than 6 characters. | Detailed Description: The password field in the login page is found to accept less than 6 characters. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Login link 4. Enter invalid password. 5. Click on Submit button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the password field is accepting less than 6 characters. | Coding | Internet Explorer | Internal Dev | High | High | 1.1 | Build 1.0 | 2018-07-17 | Siri | xxx | ACT | Test Cycle 1 | TC_NAME_03
LOGIN_003 | LOGIN | No error message is displayed even after entering invalid username and password | Detailed Description: No error message is displayed even after entering invalid username and password. Steps to reproduce a bug: 1. Open Browser 2. Enter URL for the website 3. Click on the Login link 4. Enter ivalid user name and password. 5. Click on Submit button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts invalid values in the name field and password field. The application proceeds to the next page.There is no error message shown as expected. | Coding | Internet Explorer | Internal Dev | High | High | 1.1 | Build 1.0 | 2018-07-17 | Siri | xxx | ACT | Test Cycle 1 | TC_NAME_04
LOGIN_004 | LOGIN | On clicking the submit button in the login page, no error message is being displayed for entering invalid credentials. | Detailed Description: On clicking the submit button in the login page, no error message is being displayed for entering invalid credentials. 1. Open Browser 2. Enter URL for the website 3. Click on the Login link 4. Enter invalid credentials. 5. Click on Submit button Actual result observed on running above steps: On executing the above mentioned steps it is observed that no error message is displayed after entering invalid credentials. | Coding | Internet Explorer | Internal Dev | High | High | 1.1 | Build 1.0 | 2018-07-17 | Siri | xxx | ACT | Test Cycle 1 | TC_NAME_05
REQUEST_001 | RAISE_REQUEST | Negative numbers are also accepted in the asset quantity in the "raise a request" page. | Detailed Description: When the asset quantity is entered in the "raise a request" page, there is no maximum limit set for the field. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Register link 4. Click on raise a request. 5. Enter invalid asset quantity 6. Enter other Valid credentials 7. The website should generate an asset id. 6. Click on Submit button. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the maximum limit is not set for the quantity. | Coding | Internet Explorer | Internal Dev | Medium | High | 1.1 | Build 1.0 | 2018-07-17 | Siri | xxx | ACT | Test Cycle 1 | TC_QUAN_03
REQUEST_002 | RAISE_REQUEST | Only one name is present in the dropdown list of the field asset name. | Detailed Description: Only one name is present in the dropdown list of the field asset name. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Register link 4. Click on raise a request. 5. Select asset name 6. Enter other Valid credentials 7. The website should generate an asset id. 6. Click on Submit button. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the maximum limit is not set for the quantity. | Coding | Internet Explorer | Internal Dev | Medium | High | 1.1 | Build 1.0 | 2018-07-17 | Siri | xxx | ACT | Test Cycle 1 | TC_QUAN_03
MODIFY_001 | MODIFY_ASSET | On clicking the modify asset in the web page, it is not redirecting to the correct web page | Detailed Description: On clicking the modify asset in the web page, it is not redirecting to the correct web page. Steps to reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on the login link 4. Enter other Valid credentials 5. Click on Submit button 6. Click on modify asset in the next page Actual result observed on running above steps: On executing the above mentioned steps it is observed that on clicking the button,it is not redirecting to the next page. | Coding | Internet Explorer | Internal Dev | High | High | 1.1 | Build 1.0 | 2018-07-17 | Siri | xxx | ACT | Test Cycle 1 | TC_ID_03
ASSET NAME_001 | ADD_ASSET | No error message is displayed even after entering the invalid values in the Asset name field in the add asset web page. | Detailed Description: No error message is displayed even after entering the invalid values in the Asset name field in the add asset web page. Steps to reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on the login link 4. Enter other Valid credentials 5. Enter invalid asset name 6. Click on Submit button Actual result observed on running above steps: On executing the above mentioned steps it is observed that no error message is displayed even after entering invalid values in the asset name field. | Coding | Internet Explorer | Internal Dev | High | High | 1.1 | Build 1.0 | 2018-07-17 | Siri | xxx | ACT | Test Cycle 1 | TC_ID_03
ASSET NAME_002 | ADD_ASSET | The Asset name field in the add asset web page is found to accept special characters and digits. | Detailed Description: The Asset name field in the add asset web page is found to accept special characters and digits. Steps to reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on the login link 4. Enter other Valid credentials 5. Enter invalid asset name 6. Click on Submit button Actual result observed on running above steps: On executing the above mentioned steps it is observed that special characters and digits are accepted in the asset name field. | Coding | Internet Explorer | Internal Dev | High | High | 1.1 | Build 1.0 | 2018-07-17 | Siri | xxx | ACT | Test Cycle 1 | TC_ID_03
ASSET DESC_001 | ADD_ASSET | When asset description is entered in the add asset web page,there is no word limit set. | Detailed Description: When asset description is entered in the add asset web page,there is no word limit set. Steps to reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on the login link 4. Enter other Valid credentials 5. Enter description exceeding the word limit 6. Click on Submit button Actual result observed on running above steps: On executing the above mentioned steps it is observed that no error message is displayed even after exceeding the word limit. | Coding | Internet Explorer | Internal Dev | Low | Medium | 1.1 | Build 1.0 | 2018-07-17 | Siri | xxx | ACT | Test Cycle 1 | TC_DESC_01